## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Planning
1.1 | Literature review of continuum robots | Veeresh | 2026-01-07 | 2026-01-15 | 8 | 100% | bar: WEEK 1 M to WEEK 3 T
1.2 | Define project objectives | Rishith | 2026-01-07 | 2026-01-15 | 8 | 100% | bar: WEEK 1 M to WEEK 3 T
1.3 | Define performance requirements | Arijit | 2026-01-07 | 2026-01-15 | 8 | 100% | bar: WEEK 1 M to WEEK 3 T
1.4 | System architecture planning | Arshit | 2026-01-07 | 2026-01-15 | 8 | 100% | bar: WEEK 1 M to WEEK 3 T
1.5 | Project timeline creation | Prithvi | 2026-01-07 | 2026-01-15 | 8 | 100% | bar: WEEK 1 M to WEEK 3 T
2 | Requirements & System Design
2.1 | Define degrees of freedom | Arijit | 2026-01-15 | 2026-01-26 | 11 | 100% | bar: WEEK 2 M to WEEK 4 W
2.2 | Define actuation method (tendon-driven) | Rishith | 2026-01-15 | 2026-01-26 | 11 | 100% | bar: WEEK 2 M to WEEK 4 W
2.3 | Define materials and dimensions | Arshit | 2026-01-15 | 2026-01-26 | 11 | 100% | bar: WEEK 2 M to WEEK 4 W
2.4 | Overall system block diagram | Arijit | 2026-01-15 | 2026-01-26 | 11 | 100% | bar: WEEK 2 M to WEEK 4 W
3 | Mechanical Design
3.1 | Continuum backbone design | Veeresh | 2026-01-15 | 2026-02-10 | 26 | 100% | bar: WEEK 2 M to WEEK 6 F
3.2 | Tendon routing design | Arshit | 2026-01-15 | 2026-01-31 | 16 | 100% | bar: WEEK 2 M to WEEK 5 F
3.3 | End effector (tentacle) design | Arshit, Rishith | 2026-01-15 | 2026-02-10 | 26 | 100% | bar: WEEK 2 M to WEEK 6 F
3.4 | Motor mounting design | Prithvi, Arijit | 2026-01-15 | 2026-01-31 | 16 | 100% | bar: WEEK 2 M to WEEK 5 F
4 | Electronics & Hardware
4.2 | Component selection | Arijit, Prithvi | 2026-01-07 | 2026-01-15 | 8 | 100% | bar: WEEK 1 M to WEEK 3 T
4.1 | PCB design | Arshit, Veeresh | 2026-02-15 | 2026-03-15 | 28 | 80% | bar: WEEK 7 M to WEEK 11 F
4.3 | PCB Fabrication | Arshit, Veeresh | 2026-03-15 | 2026-03-22 | 7 | 0% | bar: WEEK 11 M to WEEK 12 W
4.4 | Hardware testing | Veeresh | 2026-03-22 | 2026-03-31 | 9 | 0% | bar: WEEK 12 R to WEEK 13 F
5 | Software & Control
5.1 | GUI development | Rishith | 2026-02-01 | 2026-03-05 | 32 | 100% | bar: WEEK 4 M to WEEK 10 T
5.2 | Control algorithm implementation | Prithvi | 2026-02-01 | 2026-03-05 | 32 | 60% | bar: WEEK 4 M to WEEK 8 F
5.3 | Communication protocol implementation | Rishith | 2026-02-01 | 2026-03-05 | 32 | 40% | bar: WEEK 4 M to WEEK 8 F
6 | Fabrication & Assembly
6.1 | 3D printing parts | Rishith | 2026-03-01 | 2026-03-15 | 14 | 0% | bar: WEEK 8 M to WEEK 11 F
6.2 | Mechanical assembly | Arshit | 2026-03-15 | 2026-03-31 | 16 | 0% | bar: WEEK 10 M to WEEK 13 F
6.3 | Electronics assembly | Prithvi | 2026-03-15 | 2026-03-31 | 16 | 0% | bar: WEEK 10 M to WEEK 13 F
7 | Testing and Validation
7.1 | Functional testing | Arijit | 2026-04-01 | 2026-04-07 | 6 | 0% | bar: WEEK 14 M to WEEK 14 F
7.2 | Load testing | Veeresh | 2026-04-01 | 2026-04-07 | 6 | 0% | bar: WEEK 14 M to WEEK 14 F
7.3 | Accuracy Testing | Rishith | 2026-04-01 | 2026-04-07 | 6 | 0% | bar: WEEK 14 M to WEEK 14 F